SECTION 01305

SUBMITTAL PROCEDURES

# 1	GENERAL

## 1.1	SUMMARY (Not Applicable)

## 1.2	REFERENCES (Not Applicable)

## 1.3	SUBMITTAL CLASSIFICATION

Submittals are classified as follows:

### 1.3.1	Government Approved

Governmental approval is required for extensions of design, critical materials, deviations, equipment whose compatibility with the entire system must be checked, and other items as designated by the Contracting Officer.   Within the terms of the Contract Clause entitled "Specifications and Drawings for Construction," they are considered to be "shop drawings."

### 1.3.2	Information Only

All submittals not requiring Government approval will be for information only.  They are not considered to be "shop drawings" within the terms of the Contract Clause referred to above.

## 1.4	APPROVED SUBMITTALS

The approval of submittals by the Contracting Officer shall not be construed as a complete check, but will indicate only that the general method of construction, materials, detailing and other information are satisfactory.  Approval will not relieve the Contractor of the responsibility for any error which may exist, as the Contractor under the CQC requirements of this contract, is responsible for the dimensions and design of adequate connections, details and satisfactory construction of all work.  After submittals have been approved by the Contracting Officer, no resubmittal for the purpose of substituting materials or equipment will be given consideration unless accompanied by an explanation as to why a substitution is necessary.

## 1.5	DISAPPROVED SUBMITTALS

The Contractor shall make all corrections required by the Contracting Officer and promptly furnish a corrected submittal in the form and number of copies as specified for the initial submittal.  If the Contractor considers any correction indicated on the submittals to constitute a change to the contract, notice as required under the Contract Clause entitled "Changes" shall be given promptly to the Contracting Officer.

## 1.6	WITHHOLDING OF PAYMENT

Payment for materials incorporated in the work will not be made if required approvals have not been obtained.

# 2	PRODUCTS (Not Applicable)

# 3	EXECUTION

## 3.1	GENERAL

The Contractor shall submit all items listed on the Submittal Register (ENG Form 4288) or specified in the other sections of these specifications.  The Contracting Officer may request submittals in addition to those listed when deemed necessary to adequately describe the work covered in the respective sections.  Units of weights and measures used on all submittals shall be the same used in the contract drawings.  Submittals shall be made in the respective number of copies and to the respective addresses set forth below.  Each submittal shall be complete and in sufficient detail to allow ready determination of compliance with contract requirements.  Prior to submittal, all items shall be checked and approved by the Contractor's Quality Control (CQC) representative and each respective transmittal form (ENG Form 4025) shall be stamped, signed, and dated by the CQC representative certifying that the accompanying submittal complies with the contract requirements.  Proposed deviations from the contract requirements shall be clearly identified.  Submittals shall include items such as: Contractor's, manufacturer's, or fabricator's drawings; descriptive literature including (but not limited to) catalog cuts, diagrams, operating charts or curves; test reports; test cylinders; samples; O&M manuals including parts list; certifications; warranties and other such required submittals.  Submittals requiring Government approval shall be scheduled and made prior to the acquisition of the material or equipment covered thereby.

## 3.2	SUBMITTAL REGISTER (ENG Form 4288)

At the end of this section is one set of ENG Forms 4288 listing each item of equipment and material for which submittals are required by the specifications.  Columns "c" thru "o" have been completed by the Government.  The Contractor shall complete columns "a," "b," and "p" thru "u" and return [_____] completed copies to the Contracting Officer for approval within [_____] calendar days after Notice to Proceed for approval.   The approved submittal register will become the scheduling document and will be used to control submittals throughout the life of the contract.   This register and the progress schedules shall be coordinated.

## 3.3	SCHEDULING

Submittals covering component items forming a system or items that are interrelated shall be scheduled to be coordinated and submitted concurrently.  Certifications to be submitted with the pertinent drawings shall be so scheduled.  Adequate time (a minimum of [_____] calendar days exclusive of mailing time) shall be allowed on the register for review and approval.  No delays damages or time extensions will be allowed for time lost in late submittals.

## 3.4	TRANSMITTAL FORM (ENG Form 4025)

The sample transmittal for (ENG Form 4025) attached to this section shall be used for submitting both Government approved and information only submittals in accordance with the instructions on the reverse side of the form.  These forms will be furnished to the Contractor.  This form shall be properly completed by filling out all the heading blank spaces and identifying each item submitted.  Special care will be exercised to ensure proper listing of the specification paragraph and/or sheet number of the contract drawings pertinent to the data submitted for each item.

## 3.5	SUBMITTAL PROCEDURE

Submittals shall be made as follows:

### 3.5.1	Procedures

[_____]

### 3.5.2	Deviations

For submittals which include proposed deviations requested by the Contractor, the column "variation" of ENG Form 4025 shall be checked.  The Contractor shall set forth in writing the reason for any deviations and annotate such deviations on the submittal.  The Government reserves the right to rescind inadvertent approval of submittals containing unnoted deviations.

## 3.6	CONTROL OF SUBMITTALS

The Contractor shall carefully control his procurement operations to ensure that each individual submittal is made on or before the Contractor scheduled submittal date shown on the approved "Submittal Register."

## 3.7	GOVERNMENT APPROVED SUBMITTALS

Upon completion of review of submittals requiring Government approval, the submittals will be identified as having received approval by being so stamped and date.  [_____] copies of the submittal will be retained by the Contracting Officer and [_____] copies of the submittal will be returned to the Contractor.

## 3.8	INFORMATION ONLY SUBMITTALS

Normally submittals for information only will not be returned.  Approval of the Contracting Officer is not required on information only submittals.   These submittals will be used for information purposes.  The Government reserves the right to require the Contractor to resubmit any item found not to comply with the contract.  This does not relieve the Contractor from the obligation to furnish material conforming to the plans and specifications and will not prevent the Contracting Office from requiring removal and replacement if nonconforming material is incorporated in the work.  This does not relieve the Contractor of the requirement to furnish samples for testing by the Government laboratory or check testing by the Government in those instances where the technical specifications so prescribe.

## 3.9	STAMPS

Stamps used by the Contractor on the submittal data to certify that the submittal meets contract requirements shall be similar to the following:

________________________________________________________________________

|                               CONTRACTOR                               |

|                                                                        |

|                               (Firm Name)                              |

|                                                                        |

|                                                                        |

|                                                                        |

| _____ Approved                                                         |

|                                                                        |

|                                                                        |

| _____ Approved with corrections as noted on submittal data and/or      |

| attached sheets(s).                                                    |

|                                                                        |

|                                                                        |

|                                                                        |

| SIGNATURE:  __________________________________________________________ |

|                                                                        |

| TITLE:  ______________________________________________________________ |

|                                                                        |

| DATE:  _______________________________________________________________ |

|                                                                        |

|________________________________________________________________________|